## Strategic Plan
Strategic Theme | Objective (SMART) | KPI / Metric | Baseline | Target & Date | Initiatives / Projects | Key Milestones | Owner | Start Date | End Date | Budget (CapEx/OpEx) | Resources / Headcount | Risks & Mitigations | Dependencies | Status (RAG) | Notes
Growth | [Increase qualified leads 30% in 12 months] | MQLs / month | 800 | 1,040 by Q4 | Launch SEO + Paid Media program | Keyword map (Q1), 10 pillar pages (Q2) | Owner: Marketing |  |  | $120k OpEx | SEO specialist, copywriter | Content velocity risk → editorial calendar | Dev availability
Operational Excellence | [Reduce average ticket resolution time 25% in 2 quarters] | Avg. time to resolution (hrs) | 16 | 12 by Q2 | Implement tiered support + new help desk | Pilot (Month 1), Full rollout (Month 2) | Owner: CX |  |  | $45k OpEx | Support trainers (2 FTE) | Adoption risk → internal enablement | Vendor onboarding
Product | [Increase 90‑day retention by 10 pts by year‑end] | 90‑day retention % | 62% | 72% by Q4 | Redesign onboarding + lifecycle messaging | New onboarding flow (Q2), NPS loop (Q3) | Owner: PM |  |  | $80k OpEx | Lifecycle PM, designer | Scope creep → lock MVP & change control | Data team for events

## How to Use
Step | What to do
1. Define mission & vision | Write a concise mission (why you exist) and a customer-centric vision (what future you create).
2. Diagnose reality | Run a quick SWOT and identify 3–5 root problems/opportunities informed by data.
3. Pick strategic themes | Choose 3–4 themes (e.g., Growth, Product, Ops, People) to focus resources.
4. Set SMART objectives | Make each objective Specific, Measurable, Achievable, Relevant, Time‑bound.
5. Attach KPIs & targets | Define metric, baseline, target and due date; pick leading & lagging indicators.
6. Plan initiatives | List projects that move the KPI; include milestones, owners, budgets, timelines.
7. Govern & adapt | Set a monthly review, track status (RAG), manage risks, update the changelog.

## KPI Catalog
Metric | Definition | Formula | Data Source | Frequency | Owner
MQLs / month | Marketing qualified leads generated per month | Count of leads meeting MQL criteria | CRM/Marketing Automation | Monthly | Head of Marketing
Avg. time to resolution (hrs) | Average hours to close support tickets | Sum(hours to close)/# tickets | Help Desk | Weekly | CX Lead
90‑day retention % | Percent of users active 90 days after signup | (Users active at D90)/(New users) | Product Analytics | Monthly | PM

## Risk Register
Risk | Impact (H/M/L) | Likelihood (H/M/L) | Score (I x L) | Owner | Mitigation Plan | Trigger / Early Warning | Status

## Change Log
Date | Change Description | Requested By | Approved By